## RiskSerializationData8 (hidden)
Written By Version | 8.1.0
Serialization Major Version | 4
Serialization Minor Version | 0
Browse Record | Display Mode | Sens Graph Type | Cond Sens Settings | Scenario Settings | Selected Scenario | Distribution Options | Distribution GS | Distribution Curves | Sens Tornado Options | Sens Tornado GS | Sens Tornado Curves | Scen Tornado Options | Scen Tornado GS | Scen Tornado Curves | Sens Spider Option | Sens Spider GS | Sens Spider Curves
#NAME? | 0 | 3 |  |  | 0 | TRUE | GF1_rK0qDwEAEwARAQwjACcAPQBaAG4AbwB9AIsA6wANAQcBKwD//wAAAAAAAAEEAAAAAAgiJCIjLCMjMAAAAAEXRGlzdHJpYnV0aW9uIENvbXBhcmlzb24BAAEBEAACAAEKU3RhdGlzdGljcwMBAQD/AQEBAQEAAQEBAAQAAAABAQEBAQABAQEABAAAAAKSAAK/AAIpABxUb3RhbCBDb3N0IEVzdGltYXRpb24gLyBDT1NUAAAA/9wUPAEAAAIAAgAoAB9Ub3RhbCBDb3N0IEVzdGltYXRpb24gLyBDT1NUK1JSAAElAQAAAgACAPMA/QABAQMBmpmZmZmZqT8AAGZmZmZmZu4/AAAFAAEBAQABAQEA | #NAME?
#NAME? | 0 | 3 |  |  | 0

## CostModel+RR
Base costs and uncertainty are listed in the table below:
Cost elements | Base case | Low | Mid | High | Low | Mid | High | COST | COST+RR | Add Correlation Matrix
Number of Units | 20 | [6 empty] | 20 | 20 | @RISK Correlations | Design [fixed] in $I$4 | Installation [per unit] in $I$5 | Installation [fixed] in $I$6 | Transportation [per unit] in $I$7 | Materials [per unit] in $I$8 | Technology [per unit] in $I$9
Design [fixed] | 300000 | 80% | 100% | 120% | 240000 | 300000 | 360000 | #NAME? | #NAME? | Design [fixed] in $I$4 | 1
Installation [per unit] | 20000 | 95% | 100% | 130% | 19000 | 20000 | 26000 | #NAME? | #NAME? | Installation [per unit] in $I$5 | 0 | 1
Installation [fixed] | 200000 | 80% | 100% | 200% | 160000 | 200000 | 400000 | #NAME? | #NAME? | Installation [fixed] in $I$6 | 0 | 0.8 | 1
Transportation [per unit] | 15000 | 90% | 100% | 110% | 13500 | 15000 | 16500 | #NAME? | #NAME? | Transportation [per unit] in $I$7 | 0 | 0 | 0 | 1
Materials [per unit] | 20000 | 90% | 100% | 120% | 18000 | 20000 | 24000 | #NAME? | #NAME? | Materials [per unit] in $I$8 | 0 | 0 | 0 | 0.5 | 1
Labor [per unit] | 7500 | 75% | 100% | 200% | 5625 | 7500 | 15000 | #NAME? | #NAME? | Technology [per unit] in $I$9 | 0 | 0 | 0 | 0 | 0 | 1
RISK REGISTER | [8 empty] | #NAME?
Total Cost Estimation | 1750000 | [6 empty] | #NAME? | #NAME?
Statistical Contigency | COST | COST+RR
Base estimate | 1750000 | 1750000
Probability of meeting value of base estimate | #NAME? | #NAME?
Required confidence level | 90% | 90%
Total budget required for confidence level | #NAME? | #NAME?
Contingency required for confidence level | #NAME? | #NAME?
Contingency required for confidence level [%] | #NAME? | #NAME?

## RiskRegister
Risk Description | Risk ID | Frequency | Severity | Occurs? | Impact
Increase in labor costs | R1 | 25% | 75000 | #NAME? | #NAME?
Environmental risks | R2 | 5% | 350000 | #NAME? | #NAME?
Delays in design approvals | R3 | 15% | 40000 | #NAME? | #NAME?
Reworks | R4 | 25% | 50000 | #NAME? | #NAME?
Commissioning and turnover problems | R5 | 10% | 125000 | #NAME? | #NAME?
Inadequate reviewing | R6 | 10% | 35000 | #NAME? | #NAME?
Material specification problems | R7 | 15% | 80000 | #NAME? | #NAME?
|  |  |  | Expected | 82750
|  |  |  | Simulation | #NAME?